## Agile Product Backlog
AGILE PRODUCT BACKLOG TEMPLATE
TASK ID | THEME | USER STORY | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  |  | Sprint 1 | C. Jones | 2022-07-05 | 2022-07-17 |  |  |  | In Progress | 24
1 | Functional | As a user I want to be able to reset my password | Sprint 1 | C. Jones | 2022-07-05 | 2022-07-08 | Yes | Yes | Medium | Complete | 8 | Yes | This section is for the drop-down list
2 | Functional | As a user I want to edit items | Sprint 1 | C. Jones | 2022-07-09 | 2022-07-12 | Yes | Yes | Medium | Complete | 16 | Yes | Yes | High | Complete
3 | Functional | As an administrator I want to define KPI's for my sales team | Sprint 1 | C. Jones | 2022-07-13 | 2022-07-17 | Yes | Yes | Medium | Complete | 0 | Yes | No | Medium | In Progress
|  |  | Sprint 2 | K. Ellen | 2022-08-18 | 2022-09-06 |  |  |  | Not Started | 12 |  |  | Low | Not Started
1 | Non-functional | As a user I want to restore my current screen when the system reboots | Sprint 2 | K. Ellen | 2022-08-18 | 8/222022 | Yes | Yes | Medium | Not Started | 4 | Yes
2 | Functional | As a user I want to view my data on mobile | Sprint 2 | K. Ellen | 2022-08-23 | 2022-08-28 | Yes | Yes | Medium | Not Started | 8 | Yes
3 | Functional | As a user I wan to create a report of my data | Sprint 2 | K. Ellen | 2022-08-29 | 2022-09-06 | Yes | Yes | Medium | Not Started | 0 | Yes
Sprint 3

## Agile Product Backlog - BLANK
AGILE PRODUCT BACKLOG TEMPLATE
TASK ID | THEME | USER STORY | SPRINT # | ASSIGNED TO | START | FINISH | STATUS | PRIORITY | STORY POINTS
|  |  | Sprint 1 | All | 2022-10-17 | 2022-10-30 | Complete |  | 11
1 | Functional | As a user I want to set my goals so that my session is specific to my needs | Sprint 1 |  |  |  | Complete | High | 5 | This section is for the drop-down list
2 | Functional | As a user I want to set my target muscle group so that my session only contains workouts for that muscle group | Sprint 1 |  |  |  | Complete | High | 1 | Yes | High | Complete
3 | Functional | As a user I want to set a time range so that my session fits my schedule | Sprint 1 |  |  |  | Complete | High | 3 | No | Medium | In Progress
4 | Functional |  | Sprint 1 |  |  |  | Complete | High | 2
|  |  | Sprint 2 | All | 2022-10-31 | 2022-11-13 | Not Started |  | 14 |  | Low | Not Started
1 | Functional | As a user I want to view all the possible workouts so I can familiarize myself with them | Sprint 2 |  |  |  | Not Started | Medium | 4
2 | Functional | As a user I want to favorite a workout so I can ensure it is included in my session | Sprint 2 |  |  |  | Not Started | High | 3
3 |  |  | Sprint 2 |  |  |  | Not Started | High | 3
4 |  |  | Sprint 2 |  |  |  | Not Started | Low | 4
|  |  | Sprint 3 | Chris and Shawn | 2022-11-14 | 2022-11-27 | Not Started |  | 8
1 | Non-functional | As a user I want to use a sort button so I can sort the workouts list by muscle groups, alphabetical, and favorites | Sprint 3 |  |  |  | Not Started | Low | 3
2 |  |  | Sprint 3 |  |  |  | Not Started | High | 5